## Sheet1
Project Details | [7 empty] | Contorl Points |  |  |  | Schedules |  |  |  |  | Cost
# | Cost Center | Client | Project | Project Executive | Project Manager | Service | Contract Type | Workorder Uploaded | Frequency | Status | Schedule Variance | Worked Hours | Efforts Variance | Requiered esources | Actual Resources | Budgeted Hours | Start Date | End date | Revised Date | Work Order Amount | Budget Amount | Payment Terms | Note
1 | DOMESTIC | SATYA CONSTRUCTIONS | Construction Management System |  |  | PROJECT | RETAIL | Yes | Single | Closed | -776 | 19920 | -19720 | 0 | 3 | 200 | 01-05-2019 | 01-06-2019 | 01-01-1970 | 0 | 1,20,000.00
2 | DOMESTIC | MUNINDIA | WAREHOUSE MANAGEMENT SYSTEM |  |  | PROJECT | RETAIL | No | Single | Closed | -776 | 52416 | 610584 | 0 | 8 | 663000 | 14-05-2019 | 30-06-2019 | 01-01-1970 | 6,63,000.00 | .
3 | DOMESTIC | E V B Technologies | BIOWAX |  |  | PROJECT | RETAIL | No | Single | Closed | -776 | 49392 | 150608 | 0 | 7 | 200000 | 01-03-2019 | 31-07-2019 | 01-01-1970 | 4,00,000.00 | .
4 | PENA4 | PENA4 INC | PENA4 ROI CALCULATOR |  |  | PROJECT | RETAIL | No | Single | Closed | -776 | 0 | 6480 | 3 | 0 | 6480 | 01-08-2019 | 31-08-2019 | 01-01-1970 | 6480 | .
5 | PENA4 | PENA4 INC | PENA4 ROI CALCULATOR |  |  | HOST | FTE | No | Monthly | Closed | -776 | 0 | 11526 | 1 | 0 | 11526 | 01-08-2019 | 31-10-2019 | 01-01-1970 | 66120 | .
6 | DOMESTIC | ANNAVARAM DEVASTANAM | ANNAVARAM MMS |  |  | PROJECT | RETAIL | Yes | Single | Closed | -776 | 49392 | 100608 | 3 | 7 | 150000 | 01-03-2019 | 01-01-2020 | 01-01-1970 | 3,85,000.00 | .
7 | BRANDIX - CRS | Brandix Apparel Limited | SFCS CR's |  |  | AMS | CR | No | Monthly | Closed | -776 | 198880 | -98880 | 1 | 22 | 100000 | 16-05-2018 | 28-02-2020 | 01-01-1970 | 10000 | .
8 | BRANDIX - AMS | Brandix Apparel Limited | Server Configuation to BAI -1 |  |  | CRS | CR | No | Single | Closed | -776 | 0 | 67 | 1 | 0 | 67 | 01-01-2020 | 28-02-2020 | 01-01-1970 | 40200 | 40200 | 28
9 | BRANDIX - AMS | Brandix Apparel Limited | Server Configuration to BAI 2 |  |  | CRS | CR | No | Single | Closed | -776 | 0 | 46 | 1 | 0 | 46 | 01-02-2020 | 28-02-2020 | 01-01-1970 | 27600 | 27600 | 28
10 | DOMESTIC | MUNINDIA | WAREHOUSE MANAGEMENT SYSTEM |  |  | AMS | FTE | No | Monthly | Closed | -776 | 20672 | -672 | 1 | 4 | 20000 | 01-12-2019 | 29-02-2020 | 01-01-1970 | 20000 | . | 30
11 | DOMESTIC | Vasista | Vasista Bio Wax |  |  | PROJECT | RETAIL | No | Single | Closed | -776 | 13632 | 86368 | 3 | 3 | 100000 | 05-03-2020 | 14-03-2020 | 01-01-1970 | 0 | .
12 | DOMESTIC | GOPAL TEKNOCON PVT LTD | CONTRACT MANAGEMENT SYSTEM |  |  | AMS | RETAIL | No | Monthly | Closed | -19788.7708 | 0 | 20000 | 2 | 4 | 20000 | 01-04-2019 | 31-03-2020 | 01-01-1970 | 20000 | . | 30
13 | DOMESTIC | GOPAL TEKNOCON PVT LTD | CONTRACT MANAGEMENT SYSTEM |  |  | HOST | RETAIL | No | Monthly | Closed | -19788.7708 | 0 | 2000 | 3 | 0 | 2000 | 02-03-2019 | 31-03-2020 | 01-01-1970 | 6000 | . | 30
14 | DOMESTIC | MCV BAJAJ | MCV AUTOXPERT |  |  | AMS | RETAIL | No | Monthly | Closed | -776 | 54784 | -14784 | 5 | 8 | 40000 | 01-04-2019 | 31-03-2020 | 01-01-1970 | 40000 | . | 30
15 | DOMESTIC | BOARD OF INTERMEDIATE AP | EXAMS2021 |  |  | AMS | RETAIL | No | Single | Closed | -19788.7708 | 0 | 200000 | 0 | 5 | 200000 | 01-04-2019 | 31-03-2020 | 01-01-1970 | 3,90,000.00 | . | 45
16 | DOMESTIC | BOARD OF INTERMEDIATE AP | EXAMS2021 |  |  | HOST | RETAIL | No | Single | Closed | -19788.7708 | 0 | 9000 | 1 | 1 | 9000 | 05-03-2019 | 31-03-2020 | 01-01-1970 | 50000 | . | 45
17 | OPERATIONAL | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | RESEARCH PROJECT |  |  | OPERATIONS | RETAIL | No | Yearly | Closed | -776 | 198592 | -98592 | 0 | 29 | 100000 | 01-04-2019 | 31-03-2020 | 01-01-1970 | 1,00,000.00 | .
18 | BRANDIX - PRO | Brandix Apparel Limited | SFCS 1.0 IM |  |  | PROJECT | FTE | No | Monthly | Closed | -19788.7708 | 0 | 10368 | 6 | 7 | 10368 | 01-06-2019 | 31-03-2020 | 01-01-1970 | 11018 | . | 30
19 | DOMESTIC | U&U CONNOISSEURS INDIA P.V.T LTD | INTERVIEW BUDDY |  |  | PROJECT | FTE | No | Single | Closed | -776 | 20424 | 129576 | 0 | 3 | 150000 | 06-04-2019 | 31-03-2020 | 01-01-1970 | 3,00,000.00 | .
20 | BRANDIX - PRO | Brandix Apparel Limited | V1.0 IM |  |  | PROJECT | FTE | No | Monthly | Closed | -19788.7708 | 0 | 6000000 | 6 | 0 | 6000000 | 03-06-2019 | 30-04-2020 | 01-01-1970 | 60,00,000.00 | .
21 | Xpparel | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Xpparel |  |  | PROJECT | RETAIL | No | Single | Closed | -776 | 17232 | -7232 | 0 | 3 | 10000 | 09-09-2019 | 22-05-2020 | 01-01-1970 | 1000 | .
22 | BRANDIX - AMS | Brandix Apparel Limited | HRMSRoll-out in BAI-3 |  |  | CRS | CR | No | Single | Invoiced | -1385 | 2736 | -2320 | 0 | 3 | 416 | 04-01-2020 | 22-05-2020 | 01-01-1970 | 2,50,000.00 | 2,49,600.00 | 28
23 | BRANDIX - AMS | Brandix Apparel Limited | HRMS Change Requests in BAI 1 |  |  | CRS | CR | No | Single | Invoiced | -1382 | 3760 | -3394 | 1 | 5 | 366 | 01-02-2020 | 25-05-2020 | 01-01-1970 | 2,60,000.00 | 2,19,600.00 | 28
24 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_ SCR_3582_MAY_2020 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 113 | 3 | 0 | 113 | 19-03-2020 | 25-05-2020 | 01-01-1970 | 0 | 67800 | 30
25 | BRANDIX - AMS | Brandix Apparel Limited | HRMS Change Requests in BAI 2 |  |  | CRS | CR | No | Single | Invoiced | -1382 | 0 | 366 | 1 | 0 | 366 | 01-02-2020 | 25-05-2020 | 01-01-1970 | 2,60,000.00 | 2,19,600.00 | 28
26 | BRANDIX - AMS | Brandix Apparel Limited | HRMS Change Requests in BAI- 3 |  |  | CRS | CR | No | Single | Invoiced | -1382 | 0 | 122 | 1 | 0 | 122 | 01-02-2020 | 25-05-2020 | 01-01-1970 | 2,60,000.00 | 73200 | 28
27 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_ SCR_3164_MAY_2020 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 23 | 1 | 0 | 23 | 06-04-2020 | 28-05-2020 | 01-01-1970 | 0 | 13800 | 30
28 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_ CR_May20_3448 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 3 | 1 | 0 | 3 | 24-02-2020 | 28-05-2020 | 01-01-1970 | 0 | 1800 | 30
29 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | CIP _Packing List Sewing job Creation error_F19727 |  |  | STB | SELF | No | Monthly | Closed | -19788.7708 | 0 | 0 | 1 | 0 | 0 | 24-05-2020 | 28-05-2020 | 01-01-1970 | 0 | 0 | 0
30 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | CAD saving report showing data wrong_STB_3840 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 10 | 2 | 0 | 10 | 27-05-2020 | 29-05-2020 | 01-01-1970 | 6000 | 6000 | 30
31 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_ CR_May20 |  |  | CRS | CR | No | Monthly | Closed | -776 | 4168 | -4030 | 0 | 1 | 138 | 01-05-2020 | 30-05-2020 | 01-01-1970 | 82800 | 82800 | 30
32 | BRANDIX - CRS | Brandix Apparel Limited | Can't update Rejection Qty sewing in_STB_3816 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 12 | 1 | 0 | 12 | 28-05-2020 | 30-05-2020 | 01-01-1970 | 7200 | 7200 | 30
33 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Lot reconciliation again in Update RM_STB_3844 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 5 | 2 | 0 | 5 | 27-05-2020 | 30-05-2020 | 01-01-1970 | 3000 | 3000 | 30
34 | DOMESTIC | BOARD OF INTERMEDIATE AP | DEC | Pilla Swathi | RamakrishnaSudabathula | AMS | RETAIL | No | Single | Closed | -19788.7708 | 0 | 66 | 2 | 2 | 66 | 01-02-2020 | 31-05-2020 | 01-01-1970 | 40000 | 39600 | 45
35 | DOMESTIC | BOARD OF INTERMEDIATE AP | DEC |  |  | HOST | RETAIL | No | Single | Closed | -19788.7708 | 0 | 30 | 1 | 1 | 30 | 09-04-2020 | 31-05-2020 | 01-01-1970 | 18000 | 18000 | 45
36 | BRANDIX - AMS | Brandix Apparel Limited | SOAP calls integration with SFCS for BEB, BAI-1 &2 |  |  | CRS | CR | No | Single | Closed | -776 | 4904 | -4854 | 0 | 1 | 50 | 09-01-2020 | 31-05-2020 | 01-01-1970 | 30000 | 30000
37 | BRANDIX - AMS | Brandix Apparel Limited | Continuous Improvements |  |  | CRS | CR | No | Single | Closed | -776 | 0 | 0 | 2 | 0 | 0 | 20-05-2020 | 01-06-2020 | 01-01-1970 | 48000 | 0 | 0
38 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Sewing jobs Duplicated _STB_3545 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 15 | 2 | 0 | 15 | 29-05-2020 | 01-06-2020 | 01-01-1970 | 9000 | 9000 | 30
39 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | ESD some data not syncing_STB_3841 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 20 | 2 | 0 | 20 | 27-05-2020 | 01-06-2020 | 01-01-1970 | 12000 | 12000 | 30
40 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Order summary report not working_STB_3838 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 20 | 2 | 0 | 20 | 27-05-2020 | 01-06-2020 | 01-01-1970 | 12000 | 12000 | 30
41 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Sewing IN report Issue_STB_3818 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 24 | 2 | 0 | 24 | 28-05-2020 | 02-06-2020 | 01-01-1970 | 14400 | 14400 | 30
42 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Daily Rejection Report not working _STB_2875 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 15 | 2 | 0 | 15 | 29-05-2020 | 02-06-2020 | 01-01-1970 | 9000 | 9000 | 30
43 | BRANDIX - AMS | Brandix Apparel Limited | Payroll changes in HRMS (COVID19) - BAI -1 |  |  | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 168 | 0 | 2 | 168 | 28-05-2020 | 02-06-2020 | 01-01-1970 | 1,00,800.00 | 1,00,800.00 | 28
44 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Migration issue_STB_3591 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 24 | 2 | 0 | 24 | 29-05-2020 | 02-06-2020 | 01-01-1970 | 14400 | 14400 | 30
45 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Weekly Delivery plan dashboard data wrong_STB_3842 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 29 | 2 | 0 | 29 | 29-05-2020 | 03-06-2020 | 01-01-1970 | 17400 | 17400 | 30
46 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Excess sewing Job shows as normal _STB_3784 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 30 | 2 | 0 | 30 | 01-06-2020 | 04-06-2020 | 01-01-1970 | 18000 | 18000 | 30
47 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Daily SAH Report not Working_STB_3778 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 20 | 2 | 0 | 20 | 28-05-2020 | 04-06-2020 | 01-01-1970 | 12000 | 12000 | 30
48 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Data variations need to fix permanantly_STB_3847 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 39 | 2 | 0 | 39 | 01-06-2020 | 05-06-2020 | 01-01-1970 | 23400 | 23400 | 30
49 | BRANDIX - AMS | Brandix Apparel Limited | Payroll changes in HRMS (COVID19) - BAI -2 |  |  | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 168 | 1 | 1 | 168 | 28-05-2020 | 06-06-2020 | 01-01-1970 | 1,00,800.00 | 1,00,800.00 | 28
50 | BRANDIX - AMS | Brandix Apparel Limited | Payroll changes in HRMS (COVID19) - BAI -3 |  |  | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 168 | 1 | 0 | 168 | 28-05-2020 | 06-06-2020 | 01-01-1970 | 1,00,800.00 | 1,00,800.00 | 28
51 | BRANDIX - AMS | Brandix Apparel Limited | Payroll changes in HRMS (COVID19) - BAI -3 |  |  | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 168 | 1 | 0 | 168 | 28-05-2020 | 06-06-2020 | 01-01-1970 | 1,00,800.00 | 1,00,800.00 | 28
52 | BRANDIX - AMS | Brandix Apparel Limited | Payroll changes in HRMS (COVID19) - QCI |  |  | CRS | CR | No | Single | Invoiced | -1370 | 0 | 168 | 1 | 0 | 168 | 28-05-2020 | 06-06-2020 | 01-01-1970 | 1,00,800.00 | 1,00,800.00 | 28
53 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | SFCS communicates with outside server_STB_3775 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 96 | 2 | 0 | 96 | 01-06-2020 | 08-06-2020 | 01-01-1970 | 57600 | 57600 | 30
54 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Rejection Reversal for Cutting Category_STB_3845 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 29 | 2 | 0 | 29 | 03-06-2020 | 08-06-2020 | 01-01-1970 | 17400 | 17400 | 30
55 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Cant generate packing list_STB_3766 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 39 | 2 | 0 | 39 | 04-06-2020 | 09-06-2020 | 01-01-1970 | 23400 | 23400 | 30
56 | BRANDIX - CRS | Brandix Apparel Limited | SFCS CR's |  |  | CRS | CR | No | Monthly | Closed | -19788.7708 | 0 | 2546 | 0 | 6 | 2546 | 01-11-2017 | 10-06-2020 | 01-01-1970 | 15,27,420.00 | 15,27,600.00 | 30
57 | DOMESTIC | Elan Honda | Elan AutoXpert |  |  | PROJECT | RETAIL | No | Single | Cancelled | -19788.7708 | 0 | 300000 | 3 | 3 | 300000 | 01-01-2020 | 15-06-2020 | 01-01-1970 | 0 | . | 45
58 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Accommodate special characters _STB_3760 |  |  | SSTB | CR | No | Single | Closed | -19788.7708 | 0 | 108 | 2 | 0 | 108 | 01-06-2020 | 15-06-2020 | 01-01-1970 | 64800 | 64800 | 30
59 | DOMESTIC | BOARD OF INTERMEDIATE AP | CAMPS2021 |  |  | AMS | RETAIL | No | Single | Closed | -19788.7708 | 0 | 450 | 2 | 2 | 450 | 01-04-2019 | 30-06-2020 | 01-01-1970 | 2,70,000.00 | 2,70,000.00 | 45
60 | DOMESTIC | BOARD OF INTERMEDIATE AP | CAMPS2021 |  |  | HOST | RETAIL | No | Single | Closed | -19788.7708 | 0 | 83 | 1 | 1 | 83 | 01-03-2019 | 30-06-2020 | 01-01-1970 | 50000 | 49800 | 45
61 | DOMESTIC | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | SCHEMAX ProX | SiripurapuRamanamma | GorjaSandeep | PROJECT | RETAIL | No | Single | Closed | -776 | 133440 | 366560 | 1 | 20 | 500000 | 26-04-2019 | 30-06-2020 | 01-01-1970 | 5,00,000.00 | . | 0
62 | DOMESTIC | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | SMS |  |  | PROJECT | FTE | No | Single | Closed | -776 | 10144 | 89856 | 1 | 2 | 100000 | 15-12-2019 | 30-06-2020 | 01-01-1970 | 1,00,000.00 | . | 0
63 | DOMESTIC | MUNINDIA | Supply Chain Digitisation |  |  | PROJECT | FTE | No | Single | Cancelled | -19788.7708 | 0 | 1250 | 3 | 5 | 1250 | 04-05-2020 | 30-06-2020 | 01-01-1970 | 20,00,000.00 | 7,50,000.00 | 30
64 | BRANDIX - CRS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | CIP_STB_MAY_2020 |  |  | STB | SELF | No | Single | Closed | -19788.7708 | 0 | 0 | 0 | 9 | 0 | 26-05-2020 | 30-06-2020 | 01-01-1970 | 0 | 0 | 0
65 | DOMESTIC | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Schemax WMS |  |  | STB | CR | No | Single | Cancelled | -19788.7708 | 0 | 0 | 2 | 17 | 0 | 08-05-2020 | 10-07-2020 | 01-01-1970 | 0 | .
66 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_ CR_2932_MAY_2020 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 1179 | 0 | 4 | 1179 | 01-05-2020 | 11-07-2020 | 01-01-1970 | 0 | 7,07,400.00 | 30
67 | DOMESTIC | VARUN MOTORS PVT LTD | MARUTI VJA |  |  | PROJECT | RETAIL | No | Single | Closed | -19788.7708 | 0 | 116 | 1 | 1 | 116 | 04-07-2020 | 11-07-2020 | 01-01-1970 | 70000 | 69600 | 30
68 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_4144_AUG_2020 |  |  | SCR | RETAIL | No | Single | Closed | -19788.7708 | 0 | 52 | 0 | 1 | 52 | 11-07-2020 | 17-07-2020 | 01-01-1970 | 0 | 31200 | 30
69 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_4141_AUG_2020 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 148 | 1 | 2 | 148 | 02-07-2020 | 24-07-2020 | 01-01-1970 | 0 | 88800 | 30
70 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_CR_Hourly Efficiency New Report_4145 |  |  | SCR | RETAIL | No | Single | Closed | -1115 | 1416 | -1355 | 2 | 1 | 61 | 17-07-2020 | 28-07-2020 | 01-01-1970 | 0 | 36600 | 30
71 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_4477_AUG_2020 |  |  | SCR | CR | No | Monthly | Closed | -19788.7708 | 0 | 50 | 1 | 0 | 50 | 05-08-2020 | 15-08-2020 | 01-01-1970 | 0 | 30000 | 30
72 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_CR_AUG_2020 |  |  | CRS | CR | No | Monthly | Invoiced | -1284 | 0 | 449 | 4 | 0 | 449 | 01-08-2020 | 31-08-2020 | 01-01-1970 | 2,69,400.00 | 2,69,400.00 | 30
73 | BRANDIX - CRS | Brandix Apparel Limited | BFFAV2 POST Implementation |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 40 | 3 | 0 | 40 | 01-08-2020 | 01-09-2020 | 01-01-1970 | 0 | 24000 | 30
74 | DOMESTIC | VARUN MOTORS PVT LTD | MARUTI HYD |  |  | PROJECT | RETAIL | No | Single | Closed | -1192 | 696 | -488 | 1 | 1 | 208 | 19-08-2020 | 19-09-2020 | 01-01-1970 | 1,25,000.00 | 1,24,800.00 | 30
75 | BRANDIX - CRS | Brandix Apparel Limited | NoN_AMS_CR _CWH EKala Servers Configuration |  |  | SCR | CR | No | Single | Closed | -1115 | 0 | 24 | 1 | 0 | 24 | 25-09-2020 | 29-09-2020 | 01-01-1970 | 0 | 14400 | 30
76 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_ CR_2932_MAY_2020 |  |  | CRS | CR | No | Single | Invoiced | -1240 | 0 | 1179 | 4 | 0 | 1179 | 01-01-2020 | 14-10-2020 | 01-01-1970 | 7,07,400.00 | 7,07,400.00 | 30
77 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_ CR_OCT_2020 |  |  | CRS | CR | No | Single | Closed | -1114 | 0 | 124 | 2 | 0 | 124 | 01-10-2020 | 30-10-2020 | 01-01-1970 | 74518 | 74400 | 30
78 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_4722_NOV_2020 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 63 | 1 | 0 | 63 | 03-11-2020 | 13-11-2020 | 01-01-1970 | 0 | 37800 | 30
79 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_4590_JAN_2021 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 90 | 1 | 0 | 90 | 02-11-2020 | 18-11-2020 | 01-01-1970 | 0 | 54000 | 30
80 | BRANDIX - AMS | Brandix Apparel Limited | VS & PVH Changes in BAI-1 |  |  | CRS | CR | No | Single | Invoiced | -1193 | 440 | -248 | 0 | 1 | 192 | 25-09-2020 | 30-11-2020 | 01-01-1970 | 1,15,302.00 | 1,15,200.00 | 28
81 | DOMESTIC | JAM Global Technologies Private Limited | JAM WEBSITE |  |  | IMS | RETAIL | No | Yearly | Closed | -1154 | 0 | 275 | 1 | 0 | 275 | 01-02-2020 | 30-11-2020 | 01-01-1970 | 1,67,000.00 | 1,65,000.00 | 30
82 | BRANDIX - PRO | Brandix Apparel Limited | SFCS 2.0 CRS |  |  | CRS | FTE | No | Single | Invoiced | -1192 | 3672 | -2424 | 3 | 9 | 1248 | 01-10-2020 | 01-12-2020 | 01-01-1970 | 7,48,800.00 | 7,48,800.00 | 45
83 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_5739_DEC_2020 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 8 | 1 | 0 | 8 | 18-12-2020 | 18-12-2020 | 01-01-1970 | 0 | 4800 | 30
84 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_5605_JAN_2021 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 67 | 0 | 1 | 67 | 10-12-2020 | 21-12-2020 | 01-01-1970 | 0 | 40200 | 30
85 | OPERATIONAL | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | PRE SALES |  |  | PROJECT | FTE | No | Single | Closed | -776 | 10336 | -10236 | 0 | 2 | 100 | 01-12-2019 | 31-12-2020 | 01-01-1970 | 0 | 60000 | 90
86 | BRANDIX - AMS | Brandix Apparel Limited | Fire Evacuation Change Request |  |  | CRS | CR | No | Single | Invoiced | -1162 | 128 | -85 | 0 | 2 | 43 | 22-12-2020 | 31-12-2020 | 01-01-1970 | 25384 | 25800 | 28
87 | BRANDIX - CRS | Brandix Apparel Limited | NON _ AMS _SCR_5474_JAN_2021 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 54 | 1 | 0 | 54 | 05-01-2021 | 11-01-2021 | 01-01-1970 | 0 | 32400 | 30
88 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_5512_JAN_2021 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 43 | 1 | 0 | 43 | 05-01-2021 | 11-01-2021 | 01-01-1970 | 0 | 25800 | 30
89 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_CR_5605_5739_4722_5770_JAN_2021 |  |  | CRS | CR | No | Single | Invoiced | -1151 | 0 | 153 | 2 | 0 | 153 | 18-12-2020 | 11-01-2021 | 01-01-1970 | 1,00,800.00 | 91800 | 30
90 | DOMESTIC | GOPAL TEKNOCON PVT LTD | Attendance Tracker |  |  | PROJECT | RETAIL | No | Single | Closed | -1085 | 3720 | -3586 | 0 | 5 | 134 | 26-11-2020 | 18-01-2021 | 01-01-1970 | 80400 | 80400 | 30
91 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_4585_JAN_2021 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 164 | 1 | 2 | 164 | 05-01-2021 | 19-01-2021 | 01-01-1970 | 0 | 98400 | 30
92 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_4587_JAN_2021 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 22 | 1 | 1 | 22 | 22-01-2021 | 27-01-2021 | 01-01-1970 | 0 | 13200 | 30
93 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_JAN_4591 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 188 | 1 | 1 | 188 | 09-01-2021 | 28-01-2021 | 01-01-1970 | 0 | 1,12,800.00 | 30
94 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_4580_JAN_2021 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 46 | 1 | 0 | 46 | 22-01-2021 | 30-01-2021 | 01-01-1970 | 0 | 27600 | 30
95 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_4583_JAN_2021 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 102 | 1 | 0 | 102 | 16-01-2021 | 01-02-2021 | 01-01-1970 | 0 | 61200 | 30
96 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_5833_FEB_2021 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 68 | 0 | 1 | 68 | 30-01-2021 | 08-02-2021 | 01-01-1970 | 0 | 40800 | 30
97 | BRANDIX - CRS | Brandix Apparel Limited | 5714_Marker End-Allowance Capturing |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 50 | 0 | 1 | 50 | 28-01-2021 | 12-02-2021 | 01-01-1970 | 0 | 30000 | 30
98 | BRANDIX - CRS | Brandix Apparel Limited | 5833_5872_FEB_2021_NON_AMS_CR |  |  | CRS | CR | No | Single | Invoiced | -1118 | 0 | 106 | 1 | 0 | 106 | 30-01-2021 | 13-02-2021 | 01-01-1970 | 69600 | 63600 | 30
99 | BRANDIX - CRS | Brandix Apparel Limited | Non _AMS_CR_Jan _2021 |  |  | CRS | CR | No | Single | Invoiced | -1116 | 0 | 766 | 4 | 0 | 766 | 01-01-2021 | 15-02-2021 | 01-01-1970 | 5,52,000.00 | 4,59,600.00 | 30
100 | BRANDIX - CRS | Brandix Apparel Limited | NON_AMS_SCR_5872_FEB_2021 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 44 | 1 | 1 | 44 | 11-02-2021 | 16-02-2021 | 01-01-1970 | 0 | 26400 | 30
101 | BRANDIX - CRS | Brandix Apparel Limited | Non _ AMS _SCR_5770_JAN_2021 |  |  | SCR | CR | No | Single | Closed | -19788.7708 | 0 | 15 | 1 | 0 | 15 | 18-02-2021 | 19-02-2021 | 01-01-1970 | 0 | 9000 | 30
102 | BRANDIX - AMS | Brandix Apparel Limited | C-Shift Changes in HRMS |  |  | CRS | CR | No | Single | Invoiced | -1107 | 144 | -100 | 0 | 2 | 44 | 15-02-2021 | 24-02-2021 | 01-01-1970 | 26418 | 26400 | 28
103 | DOMESTIC | BUZOPS | BUZOPS |  |  | PROJECT | RETAIL | No | Monthly | Closed | -1106 | 336 | -36 | 5 | 2 | 300 | 02-02-2021 | 28-02-2021 | 01-01-1970 | 2,00,000.00 | 1,80,000.00 | 30
104 | BRANDIX - AMS | Brandix Apparel Limited | HRMS OT minute to Minute changes |  |  | CRS | CR | No | Single | Invoiced | -1102 | 208 | -111 | 0 | 2 | 97 | 15-02-2021 | 01-03-2021 | 01-01-1970 | 58387 | 58200 | 28
105 | DOMESTIC | MACRO MEDIA OUTDOOR SOLUTIONS PVT LTD | SAMS |  |  | AMS | RETAIL | No | Monthly | Closed | -1367 | 8832 | -8766 | 1 | 3 | 66 | 01-04-2019 | 31-03-2021 | 01-01-1970 | 40000 | 39600 | 30
106 | DOMESTIC | MACRO MEDIA OUTDOOR SOLUTIONS PVT LTD | SAMS |  |  | HOST | RETAIL | No | Monthly | Closed | -1367 | 3120 | -3110 | 1 | 1 | 10 | 06-03-2019 | 31-03-2021 | 01-01-1970 | 6000 | 6000 | 30
107 | DOMESTIC | MUNINDIA | WAREHOUSE MANAGEMENT SYSTEM |  |  | HOST | RETAIL | No | Monthly | Closed | -1071 | 4072 | -4062 | 1 | 1 | 10 | 01-08-2019 | 31-03-2021 | 01-01-1970 | 6000 | 6000 | 30
108 | BRANDIX - AMS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | CIP_PHP versioning for Indian Plant servers |  |  | SSTB | SELF | No | Single | Closed | -776 | 3944 | -2446 | 1 | 1 | 1498 | 04-06-2020 | 31-03-2021 | 01-01-1970 | 0 | 8,98,800.00 | 0
109 | OPERATIONAL | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Students Internship Training |  |  | TRANS | SELF | No | Single | Closed | -776 | 51704 | -51634 | 0 | 23 | 70 | 15-02-2021 | 31-03-2021 | 01-01-1970 | 0 | 42000 | 0
110 | DOMESTIC | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | SCHEMAX ProX |  |  | STB | RETAIL | No | Single | Closed | -1315 | 12512 | 37488 | 2 | 4 | 50000 | 26-04-2019 | 03-04-2021 | 01-01-1970 | 5,00,000.00 | 3,00,00,000.00 | 30
111 | BRANDIX - AMS | Brandix Apparel Limited | HRMS Change Requests in BAI- 3 |  |  | CRS | CR | No | Single | Closed | -776 | 0 | 6 | 1 | 0 | 6 | 20-04-2021 | 30-04-2021 | 01-01-1970 | 3181 | 3600 | 28
112 | BRANDIX - AMS | Brandix Apparel Limited | Dash board changes in BAI-1 |  |  | CRS | CR | No | Single | Invoiced | -1039 | 0 | 6 | 2 | 0 | 6 | 20-04-2021 | 03-05-2021 | 01-01-1970 | 3181 | 3600 | 28
113 | BRANDIX - AMS | Brandix Apparel Limited | Dash board changes in BAI-2 |  |  | CRS | CR | No | Single | Invoiced | -1039 | 0 | 6 | 1 | 0 | 6 | 20-04-2021 | 03-05-2021 | 01-01-1970 | 3181 | 3600 | 28
114 | BRANDIX - AMS | Brandix Apparel Limited | Dash board changes in BAi-3 |  |  | CRS | CR | No | Single | Invoiced | -1039 | 0 | 6 | 1 | 0 | 6 | 22-04-2021 | 03-05-2021 | 01-01-1970 | 3181 | 3600 | 28
115 | BRANDIX - AMS | Brandix Apparel Limited | COVID leave type changes in BAi-1 | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -1039 | 0 | 17 | 1 | 0 | 17 | 19-04-2021 | 03-05-2021 | 01-01-1970 | 9696 | 10200 | 28
116 | BRANDIX - AMS | Brandix Apparel Limited | COVID leave type changes in BAi-2 | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -1039 | 0 | 17 | 1 | 0 | 17 | 19-04-2021 | 03-05-2021 | 01-01-1970 | 9696 | 10200 | 28
117 | BRANDIX - AMS | Brandix Apparel Limited | COVID leave type changes in BAi-3 | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -1039 | 0 | 17 | 1 | 0 | 17 | 26-04-2021 | 03-05-2021 | 01-01-1970 | 9696 | 10200 | 28
118 | BRANDIX - AMS | Brandix Apparel Limited | COVID leave type changes in QCI | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -1039 | 0 | 17 | 1 | 0 | 17 | 20-04-2021 | 03-05-2021 | 01-01-1970 | 9696 | 10200 | 28
119 | BRANDIX - AMS | Brandix Apparel Limited | Test Scenario Documentations |  |  | CRS | CR | No | Single | Invoiced | -985 | 0 | 187 | 2 | 0 | 187 | 12-05-2021 | 26-06-2021 | 01-01-1970 | 93500 | 1,12,200.00 | 28
120 | BRANDIX - AMS | Brandix Apparel Limited | User Activation and Deactivation changes in HRMS - BAI-1 | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -983 | 0 | 69 | 2 | 0 | 69 | 13-05-2021 | 28-06-2021 | 01-01-1970 | 41471 | 41400 | 28
121 | BRANDIX - AMS | Brandix Apparel Limited | User Activation and Deactivation changes in HRMS - BAI-2 | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -983 | 0 | 69 | 2 | 0 | 69 | 13-05-2021 | 28-06-2021 | 01-01-1970 | 41471 | 41400 | 28
122 | BRANDIX - AMS | Brandix Apparel Limited | User Activation and Deactivation changes in HRMS - BAI-3 | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -983 | 0 | 69 | 2 | 0 | 69 | 12-05-2021 | 28-06-2021 | 01-01-1970 | 41471 | 41400 | 28
123 | BRANDIX - AMS | Brandix Apparel Limited | User Activation and Deactivation changes in HRMS - QCI | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -983 | 0 | 69 | 2 | 0 | 69 | 13-05-2021 | 28-06-2021 | 01-01-1970 | 41471 | 41400 | 28
124 | BRANDIX - CRS | Brandix Apparel Limited | PLM - Change Request |  |  | CRS | CR | No | Single | Invoiced | -981 | 576 | -131 | 0 | 3 | 445 | 03-06-2021 | 30-06-2021 | 01-01-1970 | 2,67,000.00 | 2,67,000.00 | 28
125 | BRANDIX - AMS | Brandix Apparel Limited | PHP version upgrade - BAI-3 |  |  | CRS | CR | No | Single | Invoiced | -973 | 0 | 144 | 6 | 0 | 144 | 17-05-2021 | 08-07-2021 | 01-01-1970 | 72000 | 86400 | 28
126 | BRANDIX - AMS | Brandix Apparel Limited | SFCS V 1.0 Reports & Features Training |  |  | TRANS | CR | No | Single | Invoiced | -971 | 0 | 23 | 1 | 0 | 23 | 12-04-2021 | 10-07-2021 | 01-01-1970 | 249 | 13800 | 28
127 | BRANDIX - AMS | Brandix Apparel Limited | 10days absenteeism report changes for BAI-1 |  |  | CRS | CR | No | Single | Invoiced | -964 | 0 | 8 | 1 | 0 | 8 | 10-07-2021 | 17-07-2021 | 01-01-1970 | 3098 | 4800 | 28
128 | BRANDIX - AMS | Brandix Apparel Limited | 10days absenteeism report changes for BAI-2 |  |  | CRS | CR | No | Single | Invoiced | -964 | 0 | 8 | 1 | 0 | 8 | 10-07-2021 | 17-07-2021 | 01-01-1970 | 3098 | 4800 | 28
129 | BRANDIX - AMS | Brandix Apparel Limited | 10days absenteeism report changes for BAI-3 |  |  | CRS | CR | No | Single | Invoiced | -964 | 0 | 8 | 1 | 0 | 8 | 10-07-2021 | 17-07-2021 | 01-01-1970 | 3098 | 4800 | 28
130 | BRANDIX - AMS | Brandix Apparel Limited | PHP version upgrade - BAI-2 |  |  | CRS | CR | No | Single | Invoiced | -938 | 0 | 150 | 2 | 0 | 150 | 21-07-2021 | 12-08-2021 | 01-01-1970 | 72000 | 90000 | 28
131 | BRANDIX - AMS | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Continuous Improvements in AMS |  |  | STB | SELF | No | Single | Closed | -776 | 3968 | -3368 | 1 | 1 | 600 | 01-06-2020 | 31-08-2021 | 01-01-1970 | 0 | 3,60,000.00 | 0
132 | BRANDIX - AMS | Brandix Apparel Limited | PHP version upgrade - BAI-1 |  |  | CRS | CR | No | Single | Invoiced | -919 | 400 | -250 | 2 | 2 | 150 | 03-08-2021 | 31-08-2021 | 01-01-1970 | 72000 | 90000 | 28
133 | BRANDIX - AMS | Brandix Apparel Limited | PHP version upgrade - QCI |  |  | CRS | CR | No | Single | Invoiced | -919 | 0 | 150 | 2 | 0 | 150 | 05-07-2021 | 31-08-2021 | 01-01-1970 | 72000 | 90000 | 28
134 | DOMESTIC | VARUN MOTORS PVT LTD | PADMAJA SUZUKI SALES - HYD |  |  | PROJECT | RETAIL | No | Single | Closed | -868 | 0 | 115 | 1 | 0 | 115 | 25-09-2021 | 30-09-2021 | 01-01-1970 | 70000 | 69000 | 30
135 | BRANDIX - AMS | Brandix Apparel Limited | xl & XXL sizes cr -bai-1 |  |  | CRS | CR | No | Single | Invoiced | -873 | 0 | 54 | 1 | 0 | 54 | 22-09-2021 | 16-10-2021 | 01-01-1970 | 32736 | 32400 | 28
136 | PENA4 | PENA4 INC | PENA4 IT SOFTWARE SUPPORT AND DEVELOPMENT |  |  | STAFF | FTE | Yes | Monthly | Closed | -776 | 260040 | -229885 | 0 | 33 | 30155 | 01-11-2018 | 31-10-2021 | 01-01-1970 | 27750 | .
137 | BRANDIX - AMS | Brandix Apparel Limited | SFCS V 1.0 implementation BDDKT |  |  | PROJECT | CR | No | Single | Invoiced | -852 | 0 | 172 | 2 | 0 | 172 | 05-10-2021 | 06-11-2021 | 01-01-1970 | 1,03,620.00 | 1,03,200.00 | 28
138 | DOMESTIC | BOARD OF INTERMEDIATE AP | CAMPS2021 |  |  | AMS | RETAIL | No | Single | Closed | -19788.7708 | 0 | 175 | 3 | 0 | 175 | 16-09-2021 | 15-11-2021 | 01-01-1970 | 3,15,000.00 | 1,05,000.00 | 30
139 | DOMESTIC | BOARD OF INTERMEDIATE AP | CAMPS2021 |  |  | HOST | RETAIL | No | Single | Closed | -19788.7708 | 0 | 65 | 1 | 0 | 65 | 16-09-2021 | 15-11-2021 | 01-01-1970 | 40000 | 39000 | 30
140 | BRANDIX - AMS | Brandix Apparel Limited | Job Role changes in HRMS application |  |  | CRS | CR | No | Single | Invoiced | -833 | 0 | 130 | 2 | 0 | 130 | 19-04-2021 | 25-11-2021 | 01-01-1970 | 77939 | 78000 | 28
141 | BRANDIX - AMS | Brandix Apparel Limited | IE edge support for non SFCS applictions |  |  | CRS | CR | No | Single | Invoiced | -829 | 0 | 162 | 2 | 0 | 162 | 02-10-2021 | 29-11-2021 | 01-01-1970 | 97350 | 97200 | 28
142 | DOMESTIC | FLOW CREDIT | FLOW CREDIT |  |  | STAFF | FTE | No | Monthly | Closed | -1137 | 3744 | -3654 | 1 | 4 | 90 | 07-09-2020 | 31-12-2021 | 01-01-1970 | 50000 | 54000 | 30
143 | DOMESTIC | VARUN MOTORS PVT LTD | Lakshmi Finance Vijayawada |  |  | PROJECT | RETAIL | No | Single | Closed | -766 | 0 | 360 | 2` | 0 | 360 | 01-07-2021 | 20-01-2022 | 01-01-1970 | 3,50,000.00 | 2,16,000.00 | 30
144 | BRANDIX - CRS | Brandix Apparel Limited | Employe role changes in HRMS application for BAI-1 |  |  | CRS | CR | No | Single | Invoiced | -777 | 0 | 170 | 2 | 0 | 170 | 13-12-2021 | 20-01-2022 | 01-01-1970 | 1,01,145.00 | 1,02,000.00 | 28
145 | BRANDIX - CRS | Brandix Apparel Limited | COVID dashboard in HRMS | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -777 | 0 | 37 | 2 | 0 | 37 | 15-12-2021 | 20-01-2022 | 01-01-1970 | 22216 | 22200 | 28
146 | DOMESTIC | VARUN MOTORS PVT LTD | VARUN FIN MOBILE APP | RamakrishnaSudabathula | P SravanaSandeep Reddy | PROJECT | RETAIL | No | Single | Cancelled | -738 | 1472 | -472 | 1 | 8 | 1000 | 02-02-2022 | 03-03-2022 | 01-01-1970 | 6,40,000.00 | 6,00,000.00 | 30
147 | DOMESTIC | VARUN MOTORS PVT LTD | Padmaja Accessories |  |  | PROJECT | RETAIL | No | Single | Closed | -723 | 0 | 24 | 2 | 0 | 24 | 07-03-2022 | 08-03-2022 | 01-01-1970 | 1,20,000.00 | 14400 | 30
148 | BRANDIX - CRS | Brandix Apparel Limited | Job Role changes in HRMS application for BAI-3 | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -728 | 0 | 150 | 2 | 0 | 150 | 02-02-2022 | 10-03-2022 | 01-01-1970 | 25286 | 90000 | 28
149 | DOMESTIC | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | TracX |  |  | PROJECT | SELF | No | Single | Closed | -776 | 9920 | 190080 | 2 | 2 | 200000 | 01-01-2020 | 21-03-2022 | 01-01-1970 | 1,00,000.00 | . | 0
150 | OPERATIONAL | PCB INC | PCB FTE |  |  | PROJECT | FTE | No | Monthly | Closed | -645 | 0 | 5000 | 1 | 0 | 5000 | 22-11-2021 | 22-03-2022 | 01-01-1970 | 3,50,000.00 | 30,00,000.00 | 15
151 | BRANDIX - CRS | Brandix Apparel Limited | COVID Dashboard changes in QCI | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -707 | 0 | 10 | 1 | 0 | 10 | 01-03-2022 | 31-03-2022 | 01-01-1970 | 5554 | 6000 | 28
152 | BRANDIX - CRS | Brandix Apparel Limited | Job Role changes in HRMS application for QCI | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -707 | 0 | 150 | 1 | 0 | 150 | 01-03-2022 | 31-03-2022 | 01-01-1970 | 25286 | 90000 | 28
153 | DOMESTIC | VERIS SOLUTIONS PTD LTD | JAM WEBSITE |  |  | AMS | RETAIL | No | Monthly | Closed | -1154 | 0 | 40 | 1 | 0 | 40 | 01-05-2020 | 31-03-2022 | 01-01-1970 | 1800 | 24000 | 30
154 | DOMESTIC | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | BikeWO |  |  | PROJECT | RETAIL | No | Single | Cancelled | -610 | 896 | -656 | 2 | 1 | 240 | 21-02-2022 | 31-03-2022 | 01-01-1970 | 50000 | 1,44,000.00 | 30
155 | BRANDIX - CRS | Brandix Apparel Limited | COVID Dashboard changes in BAI-2 | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -707 | 0 | 150 | 1 | 0 | 150 | 01-03-2022 | 31-03-2022 | 01-01-1970 | 5554 | 90000 | 28
156 | BRANDIX - CRS | Brandix Apparel Limited | COVID Dashboard changes in BAI-3 | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -707 | 0 | 150 | 1 | 0 | 150 | 01-03-2022 | 31-03-2022 | 01-01-1970 | 5554 | 90000 | 28
157 | BRANDIX - CRS | Brandix Apparel Limited | Job Role changes in HRMS application for BAI-2 | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -692 | 0 | 100 | 2 | 0 | 100 | 12-01-2022 | 15-04-2022 | 01-01-1970 | 25286 | 60000 | 28
158 | BRANDIX - CRS | Brandix Apparel Limited | HCM Integration to sfcs v 1.0 |  |  | CRS | CR | No | Single | Invoiced | -669 | 0 | 12 | 1 | 0 | 12 | 20-04-2022 | 08-05-2022 | 01-01-1970 | 7260 | 7200 | 28
159 | DOMESTIC | Saint-Gobain | Canteen Management System |  |  | PROJECT | CR | No | Single | Invoiced | -616 | 0 | 47 | 2 | 0 | 47 | 01-06-2022 | 30-06-2022 | 01-01-1970 | 14000 | 28200 | 30
160 | BRANDIX - CRS | Brandix Apparel Limited | HRMS Feature Roll-out to QCI |  |  | CRS | CR | No | Single | Invoiced | -604 | 0 | 235 | 2 | 0 | 235 | 01-06-2022 | 12-07-2022 | 01-01-1970 | 1,41,274.00 | 1,41,000.00 | 28
161 | BRANDIX - CRS | Brandix Apparel Limited | SFCS V 1.0 configuration at seeds | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -595 | 0 | 80 | 1 | 0 | 80 | 16-06-2022 | 21-07-2022 | 01-01-1970 | 47520 | 48000 | 28
162 | BRANDIX - CRS | Brandix Apparel Limited | Seeds Device Integration to HRMS | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -589 | 0 | 20 | 1 | 0 | 20 | 02-07-2022 | 27-07-2022 | 01-01-1970 | 12000 | 12000 | 28
163 | DOMESTIC | SIDES | CANTEEN MANAGEMENT SYSTEM | DunnaPydi Raju | ManapuramPradeep Kumar | PRODUCT | SELF | No | Single | Closed | -19788.7708 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 30-07-2022 | 01-01-1970 | 0 | 60000 | 12
164 | DOMESTIC | SIDES | UI/UX | VungaralaSekhar | Sunkari Chinnappala Naidu | PRODUCT | SELF | No | Single | Cancelled | -19788.7708 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 30-07-2022 | 01-01-1970 | 0 | 60000 | 12
165 | DOMESTIC | SIDES | TESTING | GiridaPushpa Latha | RamakrishnaSudabathula | PRODUCT | SELF | No | Single | Cancelled | -19788.7708 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 30-07-2022 | 01-01-1970 | 0 | 60000 | 12
166 | DOMESTIC | BOARD OF INTERMEDIATE AP | CAMPS-MARCH- 2022 | Pilla Swathi | RamakrishnaSudabathula | HOST | FTE | No | Single | Closed | -456 | 0 | 0 | 1 | 0 | 0 | 20-05-2022 | 20-08-2022 | 01-01-1970 | 0 | 0 | 45
167 | DOMESTIC | BOARD OF INTERMEDIATE AP | CAMPS-MAY- 2022 | Pilla Swathi | GorjaSandeep | AMS | FTE | No | Single | Closed | -458 | 0 | 120 | 3 | 0 | 120 | 17-08-2022 | 17-09-2022 | 01-01-1970 | 1,05,000.00 | 72000 | 45
168 | BRANDIX - CRS | Brandix Apparel Limited | File Creation in SFCS V 1.0 configuration | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -520 | 0 | 30 | 1 | 0 | 30 | 01-10-2022 | 04-10-2022 | 01-01-1970 | 18000 | 18000 | 28
169 | BRANDIX - CRS | Brandix Apparel Limited | HCM integration to BEL | Dakarapu Dharani Kumar | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -520 | 0 | 33 | 2 | 0 | 33 | 11-08-2022 | 04-10-2022 | 01-01-1970 | 19800 | 19800 | 28
170 | DOMESTIC | BOARD OF INTERMEDIATE AP | CAMPS-MAY- 2022 | Pilla Swathi | GorjaSandeep | HOST | FTE | No | Single | Closed | -458 | 0 | 200 | 1 | 0 | 200 | 17-08-2022 | 17-10-2022 | 01-01-1970 | 40000 | 1,20,000.00 | 45
171 | BRANDIX - CRS | Brandix Apparel Limited | Server Migration for Seeds | DunnaPydi Raju | ManapuramPradeep Kumar | CRS | CR | No | Single | Invoiced | -503 | 0 | 58 | 1 | 0 | 58 | 10-10-2022 | 21-10-2022 | 01-01-1970 | 34800 | 34800
172 | BRANDIX - CRS | Brandix Apparel Limited | SFCS Dashboard CR at Seeds | Dakarapu Dharani Kumar | ManapuramPradeep Kumar | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 67 | 2 | 0 | 67 | 06-10-2022 | 31-10-2022 | 01-01-1970 | 40000 | 40200 | 28
173 | DOMESTIC | SIDES | PRODUCTION PLANNING | GedalaBhargav | MayakuntlaSuneetha | PRODUCT | SELF | No | Single | Cancelled | -19788.7708 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 20-11-2022 | 01-01-1970 | 0 | 60000 | 12
174 | DOMESTIC | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | PHP to Tally Migration | Dakarapu Dharani Kumar | GorjaSandeep | PROJECT | SELF | No | Single | Closed | -19788.7708 | 0 | 40 | 1 | 1 | 40 | 07-11-2022 | 27-12-2022 | 01-01-1970 | 0 | 24000 | 0
175 | BRANDIX - AMS | Brandix Apparel Limited | Brandix-AMS-SL (11) |  |  | HOST | RTB | No | Monthly | Closed | -776 | 0 | 40 | 1 | 0 | 40 | 01-10-2020 | 31-12-2022 | 01-01-1970 | 24000 | 24000 | 28
176 | DOMESTIC | SIDES | IIOT | NalamRajesh | MayakuntlaSuneetha | PRODUCT | SELF | No | Single | Cancelled | -509 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 31-12-2022 | 01-01-1970 | 0 | 60000 | 12
177 | BRANDIX - CRS | Brandix Apparel Limited | 7 color pack in CPK | Dakarapu Dharani Kumar | P SravanaSandeep Reddy | CRS | CR | No | Single | Invoiced | -426 | 136 | -11 | 0 | 1 | 125 | 19-12-2022 | 06-01-2023 | 01-01-1970 | 74778 | 75000 | 0
178 | DOMESTIC | SIDES | VEHICLE REQUISITION SYSTEM | DunnaPydi Raju | GorjaSandeep | PRODUCT | SELF | No | Single | Hold | -381 | 1856 | -1756 | 3 | 4 | 100 | 12-12-2022 | 06-01-2023 | 01-01-1970 | 0 | 60000 | 12
179 | DOMESTIC | SIDES | SA_Walmart | RamakrishnaSudabathula | MatturtiEshwar | PRODUCT | SELF | No | Single | Closed | -19788.7708 | 0 | 640 | 6 | 4 | 640 | 01-07-2022 | 20-01-2023 | 01-01-1970 | 0 | 3,84,000.00 | 0
180 | DOMESTIC | SIDES | ANALYTICS & DASHBOARDS | YadavalliSrinivas | ManapuramPradeep Kumar | PRODUCT | SELF | No | Single | Hold | -400 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 30-01-2023 | 01-01-1970 | 0 | 60000 | 12
181 | BRANDIX - CRS | Brandix Apparel Limited | Data Corrections for 7 Pack CR - December | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 60 | 2 | 0 | 60 | 21-12-2022 | 31-01-2023 | 01-01-1970 | 36000 | 36000 | 28
182 | BRANDIX - CRS | Brandix Apparel Limited | Extra Shipment - 102% | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 35 | 2 | 0 | 35 | 21-12-2022 | 31-01-2023 | 01-01-1970 | 21000 | 21000 | 28
183 | DOMESTIC | SIDES | VISITOR MANAGEMENT SYSTEM | DunnaPydi Raju | P SravanaSandeep Reddy | PRODUCT | SELF | No | Single | Hold | -553 | 0 | 100 | 3 | 3 | 100 | 12-12-2022 | 04-02-2023 | 01-01-1970 | 0 | 60000 | 12
184 | BRANDIX - CRS | Brandix Apparel Limited | BERA - General shift configuration | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 27 | 0 | 1 | 27 | 27-01-2023 | 08-02-2023 | 01-01-1970 | 0 | 16200 | 1
185 | DOMESTIC | SIDES | RM WAREHOUSE | BoddedaUma Bhulaxmi | MatturtiEshwar | PRODUCT | SELF | No | Single | Closed | -534 | 0 | 100 | 3 | 0 | 100 | 10-08-2022 | 25-02-2023 | 01-01-1970 | 0 | 60000 | 12
186 | DOMESTIC | SIDES | DownTime Track_Sides | RenukaAttada | MatturtiEshwar | PRODUCT | FTE | No | Single | Closed | -19788.7708 | 0 | 120 | 2 | 0 | 120 | 14-09-2022 | 28-02-2023 | 01-01-1970 | 0 | 72000 | 30
187 | Shahi | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Sandhya | AnudeepAnudeep | P SravanaSandeep Reddy | PRODUCT | SELF | No | Single | Hold | -366 | 5088 | -5028 | 0 | 6 | 60 | 01-11-2022 | 28-02-2023 | 01-01-1970 | 36000 | 36000 | 30
188 | Shahi | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Varun | AnudeepAnudeep | P SravanaSandeep Reddy | PROJECT | SELF | No | Single | Cancelled | -19788.7708 | 0 | 60 | 0 | 2 | 60 | 16-11-2022 | 28-02-2023 | 01-01-1970 | 36000 | 36000
189 | DOMESTIC | VARUN MOTORS PVT LTD | Hospitality CRUX | Pilla Swathi | GorjaSandeep | PROJECT | SELF | No | Single | Closed | -19788.7708 | 0 | 200 | 1 | 1 | 200 | 01-02-2023 | 28-02-2023 | 01-01-1970 | 1,50,000.00 | 1,20,000.00 | 30
190 | DOMESTIC | SIDES | SCM (SALES and PROCUREMENT) | BoddedaUma Bhulaxmi | MatturtiEshwar | PRODUCT | SELF | No | Single | Closed | -19788.7708 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 28-02-2023 | 01-01-1970 | 0 | 60000 | 12
191 | DOMESTIC | SIDES | FG WAREHOUSE | PillaManisha | MatturtiEshwar | PRODUCT | SELF | No | Single | Closed | -19788.7708 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 28-02-2023 | 01-01-1970 | 0 | 60000 | 12
192 | DOMESTIC | SIDES | LOGISTIC | RaghumajjiDileep Kumar | MatturtiEshwar | PRODUCT | SELF | No | Single | Closed | -19788.7708 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 28-02-2023 | 01-01-1970 | 0 | 60000 | 12
193 | DOMESTIC | SIDES | HRMS_SIDES | DunnaPydi Raju | MatturtiEshwar | PRODUCT | SELF | No | Single | Closed | -19788.7708 | 0 | 240 | 3 | 3 | 240 | 20-07-2022 | 28-02-2023 | 01-01-1970 | 0 | 1,44,000.00 | 30
194 | DOMESTIC | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Whatsapp BroadCast | NalamRajesh | ManapuramPradeep Kumar | PROJECT | SELF | No | Single | Closed | -366 | 2400 | -2400 | 0 | 4 | 0 | 07-12-2022 | 04-03-2023 | 01-01-1970 | 0 | 0 | 28
195 | BRANDIX - CRS | Brandix Apparel Limited | MDP CR | Dakarapu Dharani Kumar | P SravanaSandeep Reddy | CRS | CR | No | Single | Invoiced | -364 | 1120 | -701 | 0 | 4 | 419 | 27-01-2023 | 09-03-2023 | 06-04-2023 | 2,51,394.00 | 2,51,400.00
196 | DOMESTIC | SIDES | SUPPLY PORTAL | RaghumajjiDileep Kumar | P SravanaSandeep Reddy | PRODUCT | SELF | No | Single | Hold | -19788.7708 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 13-03-2023 | 01-01-1970 | 0 | 60000 | 12
197 | DOMESTIC | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Asset Management | BaliAjay | KondapalliSujatha | PROJECT | SELF | No | Single | Closed | -19788.7708 | 0 | 0 | 2 | 5 | 0 | 17-02-2023 | 15-03-2023 | 01-01-1970 | 0 | 0 | 0
198 | DOMESTIC | SIDES | QA / QC | RamakrishnaSudabathula | MatturtiEshwar | PRODUCT | SELF | No | Single | Closed | -19788.7708 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 21-03-2023 | 01-01-1970 | 0 | 60000 | 12
199 | DOMESTIC | VARUN MOTORS PVT LTD | BAJAJ ACCESSORIES | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Closed | -251 | 20592 | -20576 | 2 | 2 | 16 | 01-04-2019 | 24-03-2023 | 01-01-1970 | 10000 | 9600 | 30
200 | DOMESTIC | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | Schemax Academy | GedalaBhargav | RaghumandaChandrakala | PRODUCT | SELF | No | Single | Hold | -19788.7708 | 0 | 600 | 0 | 5 | 600 | 27-02-2023 | 25-03-2023 | 25-04-2023 | 0 | 3,60,000.00 | 30
201 | BRANDIX - AMS | Brandix Apparel Limited | Brandix-AMS-SL (11) | SaraswatulaBharath | GorjaSandeep | AMS | RTB | No | Monthly | Work in progress | -343 | 332816 | -332291 | 5 | 22 | 525 | 28-01-2017 | 30-03-2023 | 01-01-1970 | 426 | 3,15,000.00
202 | DOMESTIC | SIDES | PRODUCTION CONTROL | BoddedaUma Bhulaxmi | MatturtiEshwar | PRODUCT | SELF | No | Single | Closed | -19788.7708 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 30-03-2023 | 01-01-1970 | 0 | 60000 | 12
203 | DOMESTIC | VARUN MOTORS PVT LTD | Varun FINANCE | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Work in progress | -342 | 87336 | -87303 | 3 | 9 | 33 | 01-04-2019 | 31-03-2023 | 01-01-1970 | 20000 | 19800 | 30
204 | DOMESTIC | VARUN MOTORS PVT LTD | BAJAJ SALES | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Quarterly | Work in progress | -342 | 79296 | -79251 | 3 | 8 | 45 | 01-03-2019 | 31-03-2023 | 01-01-1970 | 27000 | 27000 | 30
205 | DOMESTIC | CASA | CASA TVS | Pilla Swathi | GorjaSandeep | AMS | FTE | No | Single | Work in progress | -342 | 14112 | -14112 | 3 | 7 | 0 | 01-06-2022 | 31-03-2023 | 01-01-1970 | 0 | 0 | 0
206 | DOMESTIC | VARUN MOTORS PVT LTD | BAJAJ SALES | Pilla Swathi | GorjaSandeep | HOST | RETAIL | No | Monthly | Work in progress | -342 | 9904 | -9883 | 1 | 1 | 21 | 02-03-2019 | 31-03-2023 | 01-01-1970 | 13000 | 12600 | 30
207 | DOMESTIC | BOARD OF INTERMEDIATE AP | CAMPS-MARCH- 2022 | Pilla Swathi | GorjaSandeep | AMS | FTE | No | Single | Closed | -458 | 1312 | 4022 | 4 | 1 | 5334 | 23-05-2022 | 31-03-2023 | 01-01-1970 | 3,20,000.00 | 32,00,400.00 | 45
208 | DOMESTIC | VARUN MOTORS PVT LTD | BAJAJ ACCESSORIES | Pilla Swathi | GorjaSandeep | HOST | RETAIL | No | Monthly | Closed | -251 | 20976 | -20955 | 2 | 2 | 21 | 04-03-2019 | 31-03-2023 | 01-01-1970 | 13000 | 12600 | 30
209 | DOMESTIC | VARUN MOTORS PVT LTD | VARUN MMS | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Work in progress | -342 | 87336 | -87311 | 2 | 9 | 25 | 01-04-2019 | 31-03-2023 | 01-01-1970 | 15000 | 15000 | 30
210 | DOMESTIC | TVS - Olive | Olive TVS | Pilla Swathi | GorjaSandeep | AMS | FTE | No | Single | Work in progress | -342 | 5632 | -5482 | 5 | 4 | 150 | 01-09-2022 | 31-03-2023 | 01-01-1970 | 20000 | 90000 | 45
211 | DOMESTIC | VARUN MOTORS PVT LTD | VARUN MMS | Pilla Swathi | GorjaSandeep | HOST | RETAIL | No | Monthly | Work in progress | -342 | 9912 | -9889 | 1 | 1 | 23 | 01-03-2019 | 31-03-2023 | 01-01-1970 | 14000 | 13800 | 30
212 | DOMESTIC | VARUN MOTORS PVT LTD | Varun FINANCE | Pilla Swathi | GorjaSandeep | HOST | RETAIL | No | Monthly | Work in progress | -342 | 49560 | -49534 | 3 | 5 | 26 | 01-03-2019 | 31-03-2023 | 01-01-1970 | 16000 | 15600 | 30 | Not paying any task for this
213 | DOMESTIC | VARUN MOTORS PVT LTD | MARUTI VSP | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Work in progress | -342 | 87336 | -87320 | 2 | 9 | 16 | 01-04-2019 | 31-03-2023 | 01-01-1970 | 10000 | 9600 | 30
214 | DOMESTIC | VARUN MOTORS PVT LTD | PADMAJA SUZUKI | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Work in progress | -342 | 48520 | -48504 | 2 | 5 | 16 | 01-04-2019 | 31-03-2023 | 01-01-1970 | 10000 | 9600 | 30
215 | DOMESTIC | VARUN MOTORS PVT LTD | PADMAJA SUZUKI | Pilla Swathi | GorjaSandeep | HOST | RETAIL | No | Monthly | Work in progress | -342 | 9880 | -9859 | 1 | 1 | 21 | 06-03-2019 | 31-03-2023 | 01-01-1970 | 13000 | 12600 | 30
216 | DOMESTIC | VARUN MOTORS PVT LTD | Varun Finance Mobile Application | RamakrishnaSudabathula | KondapalliSujatha | PROJECT | SELF | No | Single | Active | -342 | 0 | 1000 | 1 | 3 | 1000 | 25-01-2024 | 31-03-2023 | 29-02-2024 | 4,00,000.00 | 6,00,000.00 | 30
217 | BRANDIX - PRO | Brandix Apparel Limited | SFCS 2.0 | ManapuramPradeep Kumar | ManapuramPradeep Kumar | PROJECT | FTE | No | Monthly | Work in progress | -342 | 354016 | -351520 | 10 | 46 | 2496 | 21-01-2020 | 31-03-2023 | 16-04-2024 | 15,00,000.00 | 14,97,600.00 | 45
218 | BRANDIX - PRO | Brandix Apparel Limited | Operation Mapping | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Closed | -199 | 0 | 149 | 1 | 0 | 149 | 29-03-2023 | 31-03-2023 | 01-01-1970 | 40000 | 89400
219 | DOMESTIC | BOARD OF INTERMEDIATE AP | BOI IPE Practicals 2023 | Pilla Swathi | Pilla Swathi | AMS | FTE | No | Monthly | Work in progress | -342 | 0 | 200 | 4 | 4 | 200 | 01-04-2023 | 31-03-2023 | 01-01-1970 | 1,40,000.00 | 1,20,000.00 | 30
220 | DOMESTIC | VARUN MOTORS PVT LTD | MARUTI HYD | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Work in progress | -342 | 22400 | -22384 | 1 | 4 | 16 | 01-12-2020 | 31-03-2023 | 01-01-1970 | 10000 | 9600 | 30
221 | DOMESTIC | VARUN MOTORS PVT LTD | MARUTI VJA | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Work in progress | -342 | 21568 | -21552 | 1 | 4 | 16 | 01-01-2021 | 31-03-2023 | 01-01-1970 | 10000 | 9600 | 30
222 | DOMESTIC | GOPAL TEKNOCON PVT LTD | Attendance Tracker | RamakrishnaSudabathula | GorjaSandeep | HOST | RETAIL | No | Quarterly | Work in progress | -342 | 0 | 5 | 1 | 0 | 5 | 01-01-2021 | 31-03-2023 | 01-01-1970 | 4500 | 3000 | 30
223 | DOMESTIC | Andhra University | AU Webportal | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Work in progress | -342 | 26000 | -25984 | 2 | 5 | 16 | 01-02-2021 | 31-03-2023 | 01-01-1970 | 10000 | 9600 | 45
224 | DOMESTIC | Andhra University | AU Webportal | RamakrishnaSudabathula | GorjaSandeep | HOST | RETAIL | No | Monthly | Work in progress | -342 | 5200 | -5184 | 1 | 1 | 16 | 01-02-2021 | 31-03-2023 | 01-01-1970 | 15424 | 9600 | 45
225 | DOMESTIC | VARUN MOTORS PVT LTD | Lakshmi Finance Vijayawada | Pilla Swathi | GorjaSandeep | HOST | RETAIL | No | Monthly | Work in progress | -342 | 0 | 26 | 1 | 0 | 26 | 01-08-2021 | 31-03-2023 | 01-01-1970 | 16000 | 15600 | 30
226 | DOMESTIC | VARUN MOTORS PVT LTD | Lakshmi Finance Vijayawada | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Work in progress | -342 | 15968 | -15935 | 1 | 4 | 33 | 01-08-2021 | 31-03-2023 | 01-01-1970 | 20000 | 19800 | 30
227 | DOMESTIC | VARUN MOTORS PVT LTD | Padmaja Accessories | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Work in progress | -342 | 10432 | -10407 | 1 | 4 | 25 | 01-03-2022 | 31-03-2023 | 01-01-1970 | 15000 | 15000 | 30
228 | DOMESTIC | MARINEX TECH INNOVATION PRIVATE LIMITED | MARINEX TECH ERP | RamakrishnaSudabathula | MatturtiEshwar | HOST | RETAIL | No | Monthly | Closed | -307 | 0 | 60 | 1 | 0 | 60 | 01-09-2022 | 06-04-2023 | 01-01-1970 | 25000 | 36000 | 30
229 | DOMESTIC | Sai Resource | Trading Software | ReddiBhanuteja | RaghumandaChandrakala | PROJECT | FTE | No | Monthly | Work in progress | -327 | 16184 | -15584 | 2 | 7 | 600 | 01-05-2022 | 15-04-2023 | 31-03-2024 | 0 | 3,60,000.00 | 30
230 | BRANDIX - PRO | Brandix Apparel Limited | Purging - BAI2 | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 121 | 1 | 0 | 121 | 11-04-2023 | 17-04-2023 | 01-01-1970 | 72600 | 72600
231 | BRANDIX - PRO | Brandix Apparel Limited | BAI1 - Data Purging | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 56 | 1 | 0 | 56 | 12-04-2023 | 18-04-2023 | 01-01-1970 | 33600 | 33600
232 | DOMESTIC | VARUN MOTORS PVT LTD | Laxmi Finance HYD | DevupalliHimabindu | KondapalliSujatha | PROJECT | SELF | No | Single | Cancelled | -19788.7708 | 0 | 118 | 1 | 0 | 118 | 01-05-2023 | 10-05-2023 | 01-01-1970 | 70000 | 70800 | 30
233 | DOMESTIC | VARUN MOTORS PVT LTD | Lakshmi Finance Hyderabad | Pilla Swathi | GorjaSandeep | PROJECT | RETAIL | No | Monthly | Closed | -19788.7708 | 0 | 0 | 2 | 0 | 0 | 18-05-2023 | 26-05-2023 | 01-01-1970 | 75000 | 0 | 0
234 | DOMESTIC | MARINEX TECH INNOVATION PRIVATE LIMITED | MARINEX TECH ERP | RamakrishnaSudabathula | MatturtiEshwar | PROJECT | RETAIL | No | Single | Closed | -307 | 140400 | -131400 | 9 | 27 | 9000 | 04-03-2021 | 30-05-2023 | 01-01-1970 | 50,00,000.00 | 54,00,000.00 | 30
235 | DOMESTIC | Sandhya Aqua Exports Private Limited | Sandhya_AMS | BoddedaUma Bhulaxmi | GorjaSandeep | AMS | RTB | No | Monthly | Work in progress | -281 | 1664 | -1664 | 7 | 8 | 0 | 01-05-2023 | 31-05-2023 | 31-03-2024 | 1,00,000.00 | 0 | 30
236 | DOMESTIC | NEON MOTORS PVT. LTD. | Neon Motors | DevupalliHimabindu | KondapalliSujatha | PROJECT | SELF | No | Single | Invoiced | -281 | 832 | -232 | 4 | 4 | 600 | 01-05-2023 | 31-05-2023 | 01-01-1970 | 3,50,000.00 | 3,60,000.00 | 30
237 | DOMESTIC | BOARD OF INTERMEDIATE AP | BOI IPE Practicals 2023 | Pilla Swathi | KondapalliSujatha | HOST | FTE | No | Monthly | Work in progress | -281 | 0 | 20 | 1 | 0 | 20 | 01-03-2023 | 31-05-2023 | 01-01-1970 | 40000 | 12000 | 30
238 | DOMESTIC | BOARD OF INTERMEDIATE AP | BOI IPE CAMPS MARCH 2023 | Pilla Swathi | Pilla Swathi | AMS | FTE | No | Monthly | Work in progress | -281 | 1568 | -1368 | 1 | 4 | 200 | 01-04-2023 | 31-05-2023 | 01-01-1970 | 2,80,000.00 | 1,20,000.00 | 30
239 | DOMESTIC | BOARD OF INTERMEDIATE AP | BOI IPE CAMPS MARCH 2023 | Pilla Swathi | Pilla Swathi | HOST | FTE | No | Monthly | Work in progress | -281 | 784 | -584 | 1 | 2 | 200 | 01-04-2023 | 31-05-2023 | 01-01-1970 | 40000 | 1,20,000.00 | 30
240 | DOMESTIC | BOARD OF INTERMEDIATE AP | BOI IPE Theory 2023 | Pilla Swathi | Pilla Swathi | HOST | FTE | No | Monthly | Work in progress | -266 | 0 | 10 | 1 | 0 | 10 | 01-03-2023 | 15-06-2023 | 01-01-1970 | 40000 | 6000 | 30
241 | DOMESTIC | Shahi Exports Private Limited | TMS | BoddedaUma Bhulaxmi | MatturtiEshwar | PROJECT | RETAIL | No | Single | Hold | -19788.7708 | 0 | 1480 | 0 | 14 | 1480 | 26-05-2023 | 26-06-2023 | 25-07-2023 | 0 | 8,88,000.00 | 30
242 | DOMESTIC | CASA | RANA TVS | Pilla Swathi | KondapalliSujatha | PROJECT | SELF | No | Monthly | Invoiced | -255 | 96 | 4 | 2 | 3 | 100 | 22-06-2023 | 26-06-2023 | 01-01-1970 | 0 | 60000
243 | DOMESTIC | BOARD OF INTERMEDIATE AP | BOI IPE Theory 2023 | Pilla Swathi | Pilla Swathi | AMS | CR | No | Single | Work in progress | -251 | 2960 | -2460 | 4 | 5 | 500 | 01-04-2023 | 30-06-2023 | 01-01-1970 | 1,45,000.00 | 3,00,000.00
244 | DOMESTIC | Shahi Exports Private Limited | SHAHI PMS | SingarapuManikanta Rahul | GorjaSandeep | PRODUCT | RETAIL | No | Single | Closed | -239 | 1848 | -1848 | 0 | 7 | 0 | 03-06-2023 | 30-06-2023 | 01-01-1970 | 0 | 0
245 | DOMESTIC | BOARD OF INTERMEDIATE AP | BOI IPASE MAY THEORY 2023 | Pilla Swathi | Pilla Swathi | AMS | FTE | No | Monthly | Work in progress | -251 | 800 | -500 | 4 | 4 | 300 | 01-06-2023 | 30-06-2023 | 01-01-1970 | 1,60,000.00 | 1,80,000.00 | 30
246 | DOMESTIC | BOARD OF INTERMEDIATE AP | BOI IPASE MAY THEORY 2023 | Pilla Swathi | Pilla Swathi | HOST | FTE | No | Monthly | Work in progress | -251 | 0 | 60 | 2 | 0 | 60 | 01-06-2023 | 30-06-2023 | 01-01-1970 | 20000 | 36000 | 30
247 | BRANDIX - CRS | Brandix Apparel Limited | Payslip Standardisation | DunnaPydi Raju | GorjaSandeep | CRS | CR | No | Single | Closed | -217 | 0 | 12 | 1 | 0 | 12 | 29-06-2023 | 30-06-2023 | 01-01-1970 | 7200 | 7200
248 | DOMESTIC | VARUN MOTORS PVT LTD | MARUTI BANGLORE | Pilla Swathi | GorjaSandeep | PROJECT | RETAIL | No | Single | Closed | -19788.7708 | 0 | 114 | 2 | 0 | 114 | 24-06-2023 | 06-07-2023 | 01-01-1970 | 68500 | 68400
249 | DOMESTIC | Shahi Exports Private Limited | Uniqlo - Unit 07 | RamakrishnaSudabathula | ManapuramPradeep Kumar | PROJECT | CR | No | Single | Invoiced | -241 | 64 | 6 | 0 | 1 | 70 | 01-07-2023 | 10-07-2023 | 01-01-1970 | 70000 | 42000 | 28
250 | DOMESTIC | Shahi Exports Private Limited | Uniqlo Unit 7 | KatikiSai Prakash | RamakrishnaSudabathula | PROJECT | RETAIL | No | Single | Cancelled | -19788.7708 | 0 | 0 | 0 | 5 | 0 | 13-07-2023 | 17-07-2023 | 01-01-1970 | 0 | 0 | 30
251 | BRANDIX - CRS | Brandix Apparel Limited | FNF CR - BAI1 | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 59 | 2 | 0 | 59 | 01-05-2023 | 19-07-2023 | 01-01-1970 | 35400 | 35400
252 | BRANDIX - CRS | Brandix Apparel Limited | FNF CR - BAI2 | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 59 | 2 | 0 | 59 | 18-05-2023 | 19-07-2023 | 01-01-1970 | 35400 | 35400
253 | BRANDIX - CRS | Brandix Apparel Limited | FNF CR - BAI3 | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 59 | 2 | 0 | 59 | 17-05-2023 | 19-07-2023 | 01-01-1970 | 35400 | 35400
254 | BRANDIX - CRS | Brandix Apparel Limited | FNF CR - BII | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 76 | 2 | 0 | 76 | 25-05-2023 | 19-07-2023 | 01-01-1970 | 45600 | 45600
255 | DOMESTIC | Shahi Exports Private Limited | GTS Dashboard - Unit 23 | YadavalliSrinivas | ManapuramPradeep Kumar | PROJECT | CR | No | Single | Invoiced | -226 | 504 | 696 | 0 | 3 | 1200 | 01-07-2023 | 25-07-2023 | 01-01-1970 | 10,00,000.00 | 7,20,000.00 | 28
256 | DOMESTIC | Sandhya Aqua Exports Private Limited | Sandhya ERP | MatturtiEshwar | MatturtiEshwar | PROJECT | RTB | No | Single | Closed | -19788.7708 | 0 | 5000 | 2 | 2 | 5000 | 01-11-2022 | 27-07-2023 | 01-01-1970 | 0 | 30,00,000.00 | 45
257 | DOMESTIC | Vaibhav Jewellers | Expenses Management | BaliAjay | RamakrishnaSudabathula | PROJECT | RETAIL | No | Single | Closed | -19788.7708 | 0 | 0 | 0 | 5 | 0 | 13-07-2023 | 27-07-2023 | 03-08-2023 | 0 | 0 | 30
258 | DOMESTIC | BOARD OF INTERMEDIATE AP | BOI IPASE MAY CAMPS 2023 | Pilla Swathi | Pilla Swathi | AMS | FTE | No | Monthly | Work in progress | -220 | 1632 | -1572 | 4 | 4 | 60 | 01-06-2023 | 31-07-2023 | 01-01-1970 | 2,70,000.00 | 36000 | 30
259 | DOMESTIC | BOARD OF INTERMEDIATE AP | BOI IPASE MAY CAMPS 2023 | Pilla Swathi | Pilla Swathi | HOST | FTE | No | Monthly | Work in progress | -220 | 0 | 60 | 2 | 0 | 60 | 01-06-2023 | 31-07-2023 | 01-01-1970 | 60000 | 36000 | 30
260 | DOMESTIC | Norlanka | Xapparel | ReddiBhanuteja | GorjaSandeep | PROJECT | RETAIL | No | Single | Work in progress | -220 | 1944 | 1885 | 6 | 9 | 3829 | 29-06-2023 | 31-07-2023 | 25-02-2024 | 22,97,640.00 | 22,97,400.00
261 | DOMESTIC | Shahi Exports Private Limited | Shahi Nike - Unit 12 | RamakrishnaSudabathula | ManapuramPradeep Kumar | PROJECT | CR | No | Single | Invoiced | -216 | 600 | 650 | 1 | 5 | 1250 | 19-07-2023 | 04-08-2023 | 21-08-2023 | 2,00,000.00 | 7,50,000.00 | 28
262 | BRANDIX - CRS | Brandix Apparel Limited | HRMS Change Requests | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Closed | -19788.7708 | 0 | 366 | 2 | 2 | 366 | 22-07-2023 | 08-08-2023 | 01-01-1970 | 2,19,600.00 | 2,19,600.00 | 0
263 | DOMESTIC | Shahi Exports Private Limited | Document Management PHASE 1 | PillaManisha | KondapalliSujatha | PROJECT | RETAIL | No | Single | Invoiced | -208 | 96 | -96 | 0 | 4 | 0 | 10-08-2023 | 12-08-2023 | 01-01-1970 | 2,50,000.00 | 0 | 0
264 | DOMESTIC | SCHEMAX EXPERT TECHNO CRAFTS PVT LTD | QAQC | Pilla Swathi | GorjaSandeep | PROJECT | RETAIL | No | Single | Hold | -211 | 1656 | -1656 | 0 | 9 | 0 | 14-07-2023 | 14-08-2023 | 01-01-1970 | 0 | 0 | 30
265 | DOMESTIC | Shahi Exports Private Limited | Documnet Scanning | ReddiBhanuteja | GorjaSandeep | PRODUCT | CR | No | Single | Hold | -19788.7708 | 0 | 0 | 4 | 6 | 0 | 28-08-2023 | 02-09-2023 | 15-09-2023 | 0 | 0 | 30
266 | DOMESTIC | VARUN MOTORS PVT LTD | Varun Asset Management | Pilla Swathi | KondapalliSujatha | PROJECT | CR | No | Single | Invoiced | -181 | 0 | 168 | 0 | 1 | 168 | 23-08-2030 | 08-09-2023 | 01-01-1970 | 1,00,000.00 | 1,00,800.00 | 0
267 | DOMESTIC | Shahi Exports Private Limited | CRM | BoddedaUma Bhulaxmi | MatturtiEshwar | PROJECT | RETAIL | No | Single | Hold | -19788.7708 | 0 | 1400 | 8 | 11 | 1400 | 25-07-2023 | 25-09-2023 | 01-01-1970 | 8,00,000.00 | 8,40,000.00 | 30
268 | DOMESTIC | Shahi Exports Private Limited | Shahi-Uniqlo-Unit-12 | BoddedaUma Bhulaxmi | MatturtiEshwar | PROJECT | RETAIL | No | Single | Closed | -19788.7708 | 0 | 150 | 1 | 6 | 150 | 16-09-2023 | 25-09-2023 | 01-01-1970 | 3,00,000.00 | 90000 | 30
269 | BRANDIX - AMS | Brandix Apparel Limited | BAI 1_AMS_NONSFCS | Dakarapu Dharani Kumar | GorjaSandeep | AMS | RTB | No | Monthly | Work in progress | -161 | 406600 | -406548 | 10 | 25 | 52 | 07-02-2017 | 28-09-2023 | 01-01-1970 | 31250 | 31200 | 28
270 | BRANDIX - AMS | Brandix Apparel Limited | BAI 1_AMS_SFCS | Dakarapu Dharani Kumar | GorjaSandeep | AMS | RTB | No | Monthly | Work in progress | -161 | 341504 | -341446 | 10 | 23 | 58 | 01-09-2017 | 28-09-2023 | 01-01-1970 | 35000 | 34800 | 28
271 | BRANDIX - AMS | Brandix Apparel Limited | BAI 2_AMS_NONSFCS | LakkojiSaibaba | GorjaSandeep | AMS | RTB | No | Monthly | Work in progress | -161 | 214656 | -214604 | 6 | 13 | 52 | 01-01-2017 | 28-09-2023 | 01-01-1970 | 31250 | 31200 | 28
272 | BRANDIX - AMS | Brandix Apparel Limited | BAI 2_AMS_SFCS | LakkojiSaibaba | GorjaSandeep | AMS | RTB | No | Monthly | Work in progress | -161 | 297216 | -297158 | 7 | 18 | 58 | 01-01-2017 | 28-09-2023 | 01-01-1970 | 35000 | 34800 | 28
273 | BRANDIX - AMS | Brandix Apparel Limited | BAI 3_AMS_NONSFCS | SaraswatulaBharath | GorjaSandeep | AMS | RTB | No | Monthly | Work in progress | -161 | 214656 | -214604 | 6 | 13 | 52 | 01-01-2017 | 28-09-2023 | 01-01-1970 | 31250 | 31200 | 28
274 | BRANDIX - AMS | Brandix Apparel Limited | QCI_AMS_NONSFCS | SaraswatulaBharath | GorjaSandeep | AMS | RTB | No | Monthly | Work in progress | -161 | 231168 | -231116 | 5 | 14 | 52 | 01-01-2017 | 28-09-2023 | 01-01-1970 | 31250 | 31200 | 28
275 | BRANDIX - AMS | Brandix Apparel Limited | QCI_AMS_SFCS | SaraswatulaBharath | GorjaSandeep | AMS | RTB | No | Monthly | Work in progress | -161 | 214656 | -214598 | 6 | 13 | 58 | 01-01-2017 | 28-09-2023 | 01-01-1970 | 35000 | 34800 | 28
276 | BRANDIX - AMS | Brandix Apparel Limited | BAIC_AMS_NONSFCS | DunnaPydi Raju | GorjaSandeep | AMS | RTB | No | Monthly | Work in progress | -161 | 99072 | -99064 | 0 | 6 | 8 | 01-01-2017 | 28-09-2023 | 01-01-1970 | 5000 | 4800 | 28
277 | BRANDIX - AMS | Brandix Apparel Limited | BAI 3_AMS_SFCS | SaraswatulaBharath | GorjaSandeep | AMS | RTB | No | Monthly | Work in progress | -159 | 314032 | -313974 | 9 | 19 | 58 | 01-01-2017 | 30-09-2023 | 01-01-1970 | 35000 | 34800 | 28
278 | DOMESTIC | SIDES | HRMS | DunnaPydi Raju | MatturtiEshwar | PRODUCT | SELF | No | Single | Cancelled | -520 | 0 | 100 | 3 | 0 | 100 | 18-07-2022 | 30-09-2023 | 01-01-1970 | 0 | 60000 | 12
279 | DOMESTIC | Shahi Exports Private Limited | INA Dash Board Implimentation | YadavalliSrinivas | KondapalliSujatha | PROJECT | SELF | No | Single | Invoiced | -152 | 480 | 270 | 0 | 4 | 750 | 20-09-2023 | 07-10-2023 | 13-10-2023 | 4,50,000.00 | 4,50,000.00
280 | DOMESTIC | Shahi Exports Private Limited | INA Central Dash Board | NalamRajesh | KondapalliSujatha | PROJECT | SELF | No | Single | Invoiced | -129 | 480 | 40 | 0 | 4 | 520 | 12-10-2023 | 30-10-2023 | 01-01-1970 | 3,00,000.00 | 3,12,000.00
281 | DOMESTIC | MK GOLD COST | MK GOLD ASSET | Pilla Swathi | KondapalliSujatha | PROJECT | RETAIL | No | Monthly | Active | -128 | 400 | -100 | 0 | 10 | 300 | 26-10-2023 | 31-10-2023 | 01-01-1970 | 0 | 1,80,000.00
282 | DOMESTIC | Shahi Exports Private Limited | Samplig | PillaManisha | MatturtiEshwar | PROJECT | RETAIL | No | Single | Ready for UAT | -112 | 1216 | -916 | 3 | 8 | 300 | 26-10-2023 | 16-11-2023 | 12-02-2024 | 6,00,000.00 | 1,80,000.00 | 30
283 | DOMESTIC | VMRDA | HRMS Payroll | DunnaPydi Raju | RaghumandaChandrakala | PRODUCT | RETAIL | No | Single | Active | -103 | 0 | 600 | 5 | 0 | 600 | 20-11-2023 | 25-11-2023 | 01-01-1970 | 2,05,000.00 | 3,60,000.00 | 30
284 | DOMESTIC | VARUN MOTORS PVT LTD | Varun MMs Automobiles | Pilla Swathi | KondapalliSujatha | CRS | RETAIL | No | Single | Invoiced | -98 | 1176 | -1076 | 1 | 7 | 100 | 07-11-2023 | 30-11-2023 | 01-01-1970 | 60000 | 60000 | 0
285 | DOMESTIC | Shahi Exports Private Limited | 8-Buyer OMS & BOT | KatikiSai Prakash | MatturtiEshwar | PROJECT | RETAIL | No | Single | Work in progress | -83 | 288 | 212 | 4 | 4 | 500 | 06-12-2023 | 15-12-2023 | 20-02-2024 | 8,00,000.00 | 3,00,000.00 | 30
286 | BRANDIX - CRS | Brandix Apparel Limited | Fabric width dump | DunnaPydi Raju | GorjaSandeep | CRS | CR | No | Single | Invoiced | -80 | 0 | 42 | 1 | 0 | 42 | 13-12-2023 | 18-12-2023 | 01-01-1970 | 25200 | 25200
287 | DOMESTIC | VARUN MOTORS PVT LTD | Varun CMS | Pilla Swathi | KondapalliSujatha | PROJECT | CR | No | Single | Invoiced | -67 | 800 | -680 | 3 | 5 | 120 | 07-12-2023 | 31-12-2023 | 01-01-1970 | 0 | 72000
288 | Shahi | Shahi Exports Private Limited | Shahi - FTE (3) | RaghumajjiDileep Kumar | KondapalliSujatha | PROJECT | FTE | No | Monthly | Work in progress | -66 | 9968 | -9760 | 4 | 7 | 208 | 01-06-2023 | 01-01-2024 | 01-01-1970 | 2,00,000.00 | 1,24,800.00 | 28
289 | Shahi | Shahi Exports Private Limited | Auto PO approval | RaghumajjiDileep Kumar | GorjaSandeep | PROJECT | RETAIL | No | Single | Work in progress | -59 | 256 | 78 | 1 | 2 | 334 | 20-12-2023 | 08-01-2024 | 01-01-1970 | 2,00,000.00 | 2,00,400.00 | 30
290 | DOMESTIC | VARUN MOTORS PVT LTD | Varun Finance Vijayawada-FTE | Pilla Swathi | KondapalliSujatha | AMS | CR | No | Single | Active | -52 | 424 | -334 | 1 | 1 | 90 | 13-11-2023 | 15-01-2024 | 01-01-1970 | 0 | 54000
291 | DOMESTIC | VMRDA | HRMS Payroll | DunnaPydi Raju | GorjaSandeep | PROJECT | RETAIL | No | Single | Invoiced | -52 | 0 | 0 | 4 | 0 | 0 | 15-12-2023 | 15-01-2024 | 01-01-1970 | 1,50,000.00 | 0 | 60
292 | BRANDIX - CRS | Brandix Apparel Limited | M3 Transsanctions report | Dakarapu Dharani Kumar | GorjaSandeep | CRS | CR | No | Single | Invoiced | -44 | 0 | 24 | 1 | 0 | 24 | 17-01-2024 | 23-01-2024 | 01-01-1970 | 0 | 14400
293 | DOMESTIC | VARUN MOTORS PVT LTD | Varun CMS | Pilla Swathi | KondapalliSujatha | CRS | CR | No | Single | Invoiced | -41 | 0 | 100 | 4 | 0 | 100 | 01-11-2023 | 26-01-2024 | 31-01-2024 | 51000 | 60000 | 30
294 | BRANDIX - CRS | Brandix Apparel Limited | BEKA Plant closure | DunnaPydi Raju | GorjaSandeep | CRS | CR | No | Single | Invoiced | -39 | 0 | 14 | 1 | 0 | 14 | 26-12-2023 | 28-01-2024 | 01-01-1970 | 0 | 8400
295 | Shahi | Shahi Exports Private Limited | AR Automation Phase -1 | RaghumajjiDileep Kumar | RaghumandaChandrakala | PROJECT | CR | No | Single | Ready for UAT | -36 | 80 | 503 | 2 | 2 | 583 | 25-01-2024 | 31-01-2024 | 14-02-2024 | 3,50,000.00 | 3,49,800.00 | 28
296 | Shahi | Shahi Exports Private Limited | Sampling PO automation | KatikiSai Prakash | GorjaSandeep | PROJECT | RETAIL | No | Single | Work in progress | -31 | 16 | 44 | 1 | 1 | 60 | 03-02-2024 | 05-02-2024 | 01-01-1970 | 60000 | 36000 | 0
297 | DOMESTIC | Shahi Exports Private Limited | BOM | RaghumajjiDileep Kumar | KondapalliSujatha | PROJECT | SELF | No | Single | Work in progress | -7 | 2400 | -2400 | 4 | 10 | 0 | 25-01-2024 | 29-02-2024 | 01-01-1970 | 0 | 0 | 0
298 | DOMESTIC | Sandhya Aqua Exports Private Limited | Sandhya_AMS | BoddedaUma Bhulaxmi | GorjaSandeep | HOST | RETAIL | No | Monthly | Work in progress | 24 | 0 | 0 | 1 | 0 | 0 | 01-05-2023 | 31-03-2024 | 01-01-1970 | 35000 | 0
299 | DOMESTIC | VARUN MOTORS PVT LTD | Laxmi Finance HYD | DevupalliHimabindu | KondapalliSujatha | AMS | SELF | No | Single | Cancelled | -19788.7708 | 0 | 35 | 1 | 4 | 35 | 01-06-2023 | 31-03-2024 | 01-01-1970 | 20000 | 21000 | 30
300 | DOMESTIC | VARUN MOTORS PVT LTD | Laxmi Finance HYD | DevupalliHimabindu | KondapalliSujatha | HOST | SELF | No | Single | Cancelled | -19788.7708 | 0 | 20 | 1 | 0 | 20 | 01-06-2023 | 31-03-2024 | 01-01-1970 | 10000 | 12000 | 30
301 | DOMESTIC | TVS - Olive | Olive TVS | Pilla Swathi | GorjaSandeep | HOST | RETAIL | No | Monthly | Work in progress | 24 | 0 | 8 | 1 | 0 | 8 | 01-03-2023 | 31-03-2024 | 01-01-1970 | 5000 | 4800
302 | DOMESTIC | VARUN MOTORS PVT LTD | PADMAJA SUZUKI SALES - HYD | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Work in progress | 24 | 7232 | -7232 | 1 | 4 | 0 | 01-07-2023 | 31-03-2024 | 01-01-1970 | 15000 | 0
303 | DOMESTIC | VARUN MOTORS PVT LTD | PADMAJA SUZUKI SALES - HYD | Pilla Swathi | GorjaSandeep | HOST | RETAIL | No | Monthly | Work in progress | 24 | 0 | 0 | 1 | 0 | 0 | 01-07-2023 | 31-03-2024 | 01-01-1970 | 10000 | 0
304 | DOMESTIC | VARUN MOTORS PVT LTD | Lakshmi Finance Hyderabad | Pilla Swathi | GorjaSandeep | AMS | RETAIL | No | Monthly | Work in progress | 24 | 8032 | -8032 | 1 | 4 | 0 | 01-06-2023 | 31-03-2024 | 01-01-1970 | 20000 | 0
305 | DOMESTIC | VARUN MOTORS PVT LTD | Lakshmi Finance Hyderabad | Pilla Swathi | GorjaSandeep | HOST | RETAIL | No | Monthly | Work in progress | 24 | 0 | 0 | 1 | 0 | 0 | 01-06-2023 | 31-03-2024 | 01-01-1970 | 10000 | 0
306 | DOMESTIC | NEON MOTORS PVT. LTD. | Neon Motors | DevupalliHimabindu | KondapalliSujatha | AMS | CR | No | Monthly | Work in progress | 24 | 0 | 30 | 2 | 0 | 30 | 01-07-2023 | 31-03-2024 | 01-01-1970 | 0 | 18000
307 | DOMESTIC | CASA | RANA TVS | Pilla Swathi | KondapalliSujatha | AMS | CR | No | Monthly | Work in progress | 24 | 0 | 30 | 2 | 0 | 30 | 01-07-2023 | 31-03-2024 | 01-01-1970 | 0 | 18000
308 | DOMESTIC | VARUN MOTORS PVT LTD | Varun Asset Management- FTE | Pilla Swathi | KondapalliSujatha | AMS | FTE | No | Monthly | Work in progress | 24 | 3200 | -3200 | 1 | 2 | 0 | 01-08-2023 | 31-03-2024 | 01-01-1970 | 0 | 0 | 0
309 | DOMESTIC | VARUN MOTORS PVT LTD | Asset Management - FTE | Pilla Swathi | KondapalliSujatha | CONSULTANCY | FTE | No | Monthly | Cancelled | -19788.7708 | 0 | 0 | 1 | 0 | 0 | 01-09-2023 | 31-03-2024 | 01-01-1970 | 15000 | 0 | 28
310 | BRANDIX - FMS | Brandix Apparel Limited | BAI-1 FMS | DunnaPydi Raju | GorjaSandeep | Facility Management Services | RTB | No | Monthly | Work in progress | 25 | 0 | 150 | 5 | 0 | 150 | 01-04-2023 | 01-04-2024 | 01-01-1970 | 16,10,763.00 | 90000 | 28
311 | BRANDIX - FMS | Brandix Apparel Limited | BAI- 2 FMS | DunnaPydi Raju | GorjaSandeep | Facility Management Services | RTB | No | Monthly | Work in progress | 25 | 0 | 235 | 26 | 0 | 235 | 01-04-2023 | 01-04-2024 | 01-01-1970 | 16,27,284.00 | 1,41,000.00 | 28
312 | BRANDIX - FMS | Brandix Apparel Limited | BAI -3 FMS | DunnaPydi Raju | GorjaSandeep | Facility Management Services | RTB | No | Monthly | Active | 25 | 0 | 235 | 26 | 0 | 235 | 01-04-2023 | 01-04-2024 | 01-01-1970 | 12,72,090.00 | 1,41,000.00 | 28
313 | BRANDIX - FMS | Brandix Apparel Limited | BII - FMS | DunnaPydi Raju | GorjaSandeep | Facility Management Services | RTB | No | Monthly | Work in progress | 25 | 0 | 235 | 26 | 0 | 235 | 01-04-2023 | 01-04-2024 | 01-01-1970 | 17,09,887.00 | 1,41,000.00 | 28
314 | BRANDIX - FMS | Brandix Apparel Limited | BIAC - FMS | DunnaPydi Raju | GorjaSandeep | Facility Management Services | RTB | No | Monthly | Work in progress | 25 | 0 | 235 | 26 | 0 | 235 | 01-04-2023 | 01-04-2024 | 01-01-1970 | 3,79,975.00 | 1,41,000.00 | 28
315 | DOMESTIC | BMR Group | BMR_AQUA | BoddedaUma Bhulaxmi | MatturtiEshwar | PROJECT | RETAIL | No | Single | Active | 44 | 3024 | -1224 | 2 | 7 | 1800 | 15-02-2024 | 20-04-2024 | 01-01-1970 | 14,00,000.00 | 10,80,000.00 | 30
316 | Shahi | Shahi Exports Private Limited | SHAHI-FTE(UNIT 12) | ReddiBhanuteja | KondapalliSujatha | CONSULTANCY | FTE | No | Monthly | Active | 85 | 0 | 100 | 1 | 0 | 100 | 01-02-2024 | 31-05-2024 | 01-01-1970 | 1,00,000.00 | 60000 | 45
317 | DOMESTIC | Shahi Exports Private Limited | Shivamogga - FTE | KilaparthiYernaiduK | KondapalliSujatha | PROJECT | FTE | No | Monthly | Closed | -19788.7708 | 0 | 0 | 1 | 0 | 0 | 01-08-2023 | 21-06-2024 | 01-01-1970 | 1,00,000.00 | 0 | 30
318 | TEEJAY | TEEJAY | TEEJAY FMS | DunnaPydi Raju | P SravanaSandeep Reddy | Facility Management Services | RETAIL | No | Monthly | Active | 178 | 0 | 0 | 6 | 0 | 0 | 01-09-2023 | 01-09-2024 | 01-01-1970 | 1,48,285.00 | 0 | 14
319 | DOMESTIC | VMRDA | HRMS Payroll | DunnaPydi Raju | GorjaSandeep | AMS | RETAIL | No | Monthly | Active | 279 | 0 | 100 | 1 | 0 | 100 | 03-01-2024 | 11-12-2024 | 01-01-1970 | 1,20,000.00 | 60000
320 | DOMESTIC | VARUN MOTORS PVT LTD | MARUTI HYD | Pilla Swathi | GorjaSandeep | HOST | FTE | No | Monthly | Work in progress | 896 | 0 | 165 | 1 | 0 | 165 | 01-12-2021 | 20-08-2026 | 01-01-1970 | 13000 | 99000 | 30